## 2013 Mitigation Plan MASTER
Process Requirement | Potential Disaster Scenario | Affected System | Date From | Date To | Likelihood | Impact | Affected Stakeholders | Mitigation Strategy | Mitigation Resource(s) Required | Comments | Division
Election | Office Evacuation, e.g. Bomb Threat | All Systems | 2015-10-12 | 2015-11-03 | Low | Critical | All Elections related stakeholders: Voters, Media, Counties | Establish and equip a fall back location | Off-site location(s) | Need to establish a fully-functional fall back location for key staff. This could be at another agency or a county office. | ED
Election | Weather Event/Natural Disaster, e.g. Blizzard, Flood, Fire | All Systems | 2015-10-12 | 2015-11-03 | Medium | Medium | Voters, Media, Counties | Provide additional remote access, including telephones, to key staff | CDOS IT; Off-site location(s) | Need to establish a fully-functional fall back location for key staff. This could be at another agency or a county office. | ED
Election | Gov declares state of emergency | All Systems | 2015-10-12 | 2015-11-03 | Low | High | Voters, Media, Counties | Be prepared to operate out of alternate locations. Have media strategy prepared. | Off-site location | Need to establish a fully-functional fall back location for key staff. This could be at another agency or a county office. | ED
Election | VSPC/election hours extended by CO | County Voting Process | 2015-10-12 | 2015-11-03 | Medium | Low | General Public, County Clerks, SoS, Candidates/Campaigns, Media | Talk to AG re legal strategy | Judd Choate; Legal team | This may not be a "disaster" but we should prepare. Work with court to ensure all counties stay open not just affected counties. Can this be done through AGs in advance of election? | ED
OLVR at VSPC and ballot look up | GoVote site down | GoVote site | 2015-10-12 | 2015-11-03 | Medium | Medium | Voters/County staff | CDOS IT fail-safe procedures | Trevor Timmons |  | VR
Adequate staff to process incoming VR forms | Multiple members of the team are absent for more than one day due to health/weather | Voter Registration | 2015-10-12 | 2015-11-03 | Possible | Critical | CDOS/Counties/Electors | Train multiple team members on the VR sorting and batch scan process | Minerva Padron; Time from members on the ballot access and campaign finance teams |  | VR
OLVR must be accessible 24/7 | The main OIT connection fails | Internet/GoVote site | 2015-10-12 | 2015-11-03 | Likely | Critical | CDOS/Counties/Electors | Consult with IT | Trevor Timmons |  | VR
OLVR Classic and Mobile must be available 24/7 | CDOS IT releases a "broken" update. | OLVR @ SoS | 2015-10-12 | 2015-11-03 | Possible | Critical | CDOS/Counties/Electors | If CDOS IT executes a release update they must first communicate with CDOS Managers and Media Relations for approval. Resources within IT work to address the functionality issues | Trevor Timmons, Jeff Oliver, Rich Schliep, Judd Choate, Lynn Bartels, Tim Griesmer, Minerva Padron, Dwight Shellman, Trent Parker, Vicky Stecklein |  | VR
Send VR forms to the counties. | Long-term power loss and are unable to send forms to the counties through SCORE. | Power @ Engility, Power @ SoS | 2015-10-12 | 2015-11-03 | Low | Critical | CDOS/Counties/Electors | Leverage other agencies. Deliver forms to counties through mail or by hand. Worst case: provisional ballots | Mailing supplies, vehicles for delivery, Minerva Padron |  | VR
OLVR must be accessible 24/7 | We are forced to take down SCORE for maintenance | SCORE | 2015-10-12 | 2015-11-03 | Unlikely | Critical | CDOS/Counties/Electors | Use low traffic times (late night/early morning) for SCORE maintenance | Engility, CDOS IT, SCORE Team |  | VR
OLVR must be accessible 24/7 | The OLVR application goes down. | SoS OLVR system | 2015-10-12 | 2015-11-03 | Likely | Critical | CDOS/Counties/Electors | Consult with IT | CDOS IT |  | VR
OLVR must be available and working through Election Day | OLVR goes down for extended period | SoS OLVR system | 2015-10-12 | 2015-11-03 | Moderate | Moderate to High | General Public, SoS | Minimize changes to OLVR; ensure backup internet connection is working | CDOS IT |  | VR
DEO voter lookup | DEO voter look up site fails | DEO site failure | 2015-10-12 | 2015-11-03 | Medium | Low | Voters/DEOs | Inform DEO's to direct all inquiries to SoS or counties for direct SCORE access | Minerva Padron |  | VS
Election Night Reporting | Site failure | ENR @ SOE | 2015-11-03 | 2015-11-04 | Low | Medium | Voters, Media, Counties | Contact SOE for contingency plan/build response plan | Dwight Shellman, Joel Albin, Danny Casias |  | VS
ENR website must remain accessible throughout election night | A denial of service attack or other interruption makes the site inaccessible | ENR @ SOE | 2015-11-03 | 11/415 | Low | Very High | General Public, Media, Candidates/Campaigns | Contact SOE for contingency plan/build response plan | Dwight Shellman, Joel Albin, Danny Casias |  | VS
VSPC Login | Election workers don't have voting equipment passwords or forgot passwords | DREs and Optical Scanners | 2015-10-12 | 2015-11-03 | Not Likely | Critical | County staff/voters | County staff must ensure that the passwords they give the election workers work on the equipment before it is deployed, and that runners are available to assist election workers. | County election staff | Electors will be provided provisional ballots if county location(s) experience any functionality issues. | VS
VSPC Voting | DRE or Optical Scanner loses power; VVPAT runs out of paper | DRE/Optical Scanner/VVPAT | 2015-10-12 | 2015-11-03 | Low | Low | Voters/Election Judges/County staff | County staff must ensure that VSPC has extra ballots on hand | Election Judges/County Staff |  | VS
Phone Support | Loss of power at SOS office | SoS Power | 2015-10-12 | 2015-11-03 | Low | High | Voters, Media, Counties | Redirect calls to another agency or a county | Establish off-site location |  | VS
VSPC Voting | Loss of power at SOS office | SoS/County/Engility | 2015-10-12 | 2015-11-03 | Low | Critical | Voters/Election Judges/County staff | All Hands Emergency Conference Call: Engility and CDOS IT will provide Crisis Command Lead, County Response Team Lead and SCORE Application Ops with an update on actions. An update every 15 minutes is REQUIRED until the system is operational. Crisis Command Lead conducts conference call with county and state government leadership. All team members are required to participate. Focus is on the event, current actions to remedy, and addressing questions and issues from the event. | Establish off-site location | SOS , All Ops, All Team Members and County Clerks are provided with an update. | VS
VSPC Voting | Extended loss of power at SOS office | SoS/County/Engility | 2015-10-12 | 2015-11-03 | Low | Critical |  | Crisis Management: Crisis Command Lead works with Engility, OIT, CDOS IT, SCORE Application Ops and County Response Team Lead to determine the cause and resolve the issue. Communication Lead provides an update every 30 minutes to the counties. Via email or back to the call list if necessary. County Response Team provides operational support for counties using contingency plans. | Establish off-site location | Update to all counties every 30 minutes on the outage Leadership updated every 30 minutes. | VS
VSPC Voting |  | SoS/County/Engility | 2015-10-12 | 2015-11-03 |  |  |  | Operations Resume: Crisis Command Lead notifies SOS. Crisis Command Lead conducts conference call with county and state government leadership to summarize necessary actions to resume operations. All team members are required to participate. Crisis Command Lead instructs Media Relations to work with media about resolution, impact and mitigation. CDOS IT Ops Lead notifies OIT of resolution and action plan. County Response Team to provide operational support for counties to help counties resume operations. Engility Production Ops, CDOS IT Ops, and Crisis Command Lead discuss root cause and initiate audit. | See Above | Instructions issued to the team and counties to resume business operations. Audit of outage initiated to reduce chance of further failure. | VS
SCORE Access | The main OIT connection and the alternate ISP both fail at the same time, making SCORE unavailable | Internet | 2015-10-12 | 2015-11-03 | Possible | Critical | CDOS/Petition Proponents | Prepare for CDOS to conduct verification alongside IDS in order to recover lost time when OIT issue resolved; Consult AG's office on legal remedies if unable to meet the deadline. Pollbook printed out or stored as PDF | CDOS I.T. equipment and staffing; Temp agency resources | The statutory default in the event CDOS fails to meet its 30-day deadline is to place the proposed measure on the ballot. | BA
SoS must compile, total, and post primary and general election results. | Network failure would make the database unavailable for completing this work. | Internet | 2015-11-03 | 2015-11-04 | Possible | Problematic but not critical | CDOS/General Public | Total returns by hand to determine whether automatic recounts are required; post results when the issue is resolved | Additional CDOS staff to assist totaling returns by hand | The critical piece is to ensure there is a clear winner in each race, not posting of results. | BA
SoS must verify petition signatures within 30 days of receipt of an initiative petition. | IDS (Pueblo) loses power and cannot access SCORE to conduct verification | IDS loss of power | 2015-01-01 | 2015-09-01 | Possible | Critical | CDOS/Petition Proponents | Set up computer stations in Aspen Room; Bring in temp workers and complete verification at CDOS | CDOS I.T. equipment and staffing; Temp agency resources | CDOS currently works with a temp agency, which could be leveraged to find the staff needed to take over verification. | BA
SoS must verify candidate petition signatures before statutory deadline. | Same issues identified for initiative petitions | IDS loss of power | 2015-03-31 | 2015-09-01 | Possible | Critical | CDOS/Candidates | Prepare for internal petition verification to commence when problem resolved; Consult AG's office on legal remedies if unable to meet the deadline | CDOS I.T. equipment and staffing; Temp agency resources | The statute does not address what happens if CDOS is unable to meet its verification deadlines. | BA
SoS must certify statewide ballot content to the counties for the primary and general elections. | Power, network, or database failure would make the database unavailable for completing this work. | Ballot Content | 2015-04-25 | 2015-09-01 | Possible | Critical | CDOS/Counties |  |  | Creating ballot certifications is a long process, but a failure of the database on the days leading up to the deadline would create a critical issue, because the certifications are not generated until the day before they are mailed to the counties. | BA
SoS must compile, total, and post primary and general election results. | Power failure would make the database unavailable for completing this work. | Power @ Engility, Power @ SoS | 2015-11-03 | 2015-11-05 | Possible | Problematic but not critical | CDOS/Electorate | Total returns by hand to determine whether automatic recounts are required; post results when the issue is resolved | Additional CDOS staff to assist totaling returns by hand | The critical piece is to ensure there is a clear winner in each race, not posting of results. | BA
Valid/In Sync Ballot Styles | A county regenerates ballot styles after proofing. | County Ballot Generation Process | 2015-09-01 | 2015-10-12 | Not Likely | Critical | Counties State ENR Tabulation BOD etc. | Monitor when ballot styles were last generated. Turn off privilege. Report and confirm that proofing will take place after regenerating styles. | Kathy Overman, Ben Stuart, Vicky Stecklein |  | SR
SCORE - In Person Voting through webSCORE module | Screen Freezing | SCORE @ Local | 2015-10-12 | 2015-11-03 | Likely | High | CDOS/Engility/Counties/Electors | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
SCORE - In Person Voting through webSCORE module | Connectivity Issues - Random Disconnects | Internet | 2015-10-12 | 2015-11-03 | Likely | High | CDOS/Engility/Counties/Electors | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team | Electors will be provided mail ballots if SCORE Classic is available. Electors will be provided provisional ballots if county location(s) experience any functionality issues which make it impossible to issue ballots from the system. | SR
SCORE Access | State network outage - OIT - SCORE unavailable | Internet | 2015-10-12 | 2015-11-03 | Possible | Critical | CDOS/Counties/Electors/OIT/Engility | Engility Production Ops or CDOS IT Ops communicates outage immediately to SCORE Customer Support, CDOS Managers and Media Relations verifying outage and expected downtime. Engility Production Ops has 15 minutes to verify outage impact and recovery possibility. CDOS IT Ops assists in determination of the outage and recovery timeline. Engility Production Ops or CDOS IT Ops update SCORE Customer Support, CDOS Managers and Media Relations every 30 minutes until issue is resolved. | Trevor Timmons, Jeff Oliver, Rich Schliep, Judd Choate, Lynn Bartels, Tim Griesmer, Dwight Shellman, Trent Parker, Vicky Stecklein |  | SR
SCORE - Election Cycle | Connectivity Issues - Random Disconnects | Internet | 2015-09-01 | 2015-12-04 | Likely | Critical | CDOS/Engility/Counties | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
SCORE - Election Day | Connectivity Issues - Random Disconnects | Internet | 2015-10-12 | 2015-11-03 | Possible/Likely | Critical | CDOS/Engility/Counties/Electors | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
SCORE Access | Engility Production Ops verify a system-wide outage impacting all counties | SCORE @ Engility | 2015-10-12 | 2015-11-03 | Unlikely | Critical | CDOS/Counties/Electors | Crisis Command Lead has authority to execute this plan and subsequent action. Once this decision is made, there will be no further discussion about who is in charge of managing the crisis. Engility Production Ops has 15 minutes to verify outage impact and recovery possibility. CDOS IT Ops assists in determination of the outage and recovery timeline. County Response Team Lead calls county response team together for direction. County Response Team Lead will direct Communication Lead to immediately email all counties of outage and instruct counties to stand by. Communication to be sent will be provided. If internet connectivity is down to counties - use County Response Team phone calls. | Crisis Command Lead - TBD County Response Team Lead - Vicky Stecklein County Response Team - Paula Barnett Josh Johnson Ryan Schriner Dwight Shellman Ben Schler Communication Lead - TBD (Lisa Doran?) CDOS IT Ops - Trevor Timmons CIO/Rich Schliep Engility Production Ops - Karla Lewis/Greg Walker SCORE Application Ops Lead - Trent Parker | Summary Actions: Crisis Command Assigned Assembly of County Response Team County Broadcast of Outage Recovery Assessment | SR
SCORE Access | Engility Production Ops and CDOS IT Ops declare recovery is greater than 30 minutes | SCORE @ Engility | 2015-10-12 | 2015-11-03 | Unlikely | Critical | CDOS/Counties/Electors | Crisis Command Lead notifies County Response Team Lead. Crisis Command Lead notifies SOS. Crisis Command Lead instructs Media Relations to release outage and contingency press release. Press release to be provided. Engility Production Ops Lead and CDOS IT Ops Lead notify OIT Leadership of system failure and contingency actions. CDOS IT Ops Lead sets a conference call with OIT, Engility, Crisis Command Lead, County Response Team Lead, SCORE Application Ops Lead, to summarize actions within 15 minutes. County Response Team Lead calls county response team together for direction. County Response Team Lead will direct Communication Lead to immediately email all counties of outage and instruct counties to stand by. Communication to be sent will be provided. County Response Team conducts outbound calls to assigned counties to communicate system outage and that system recovery is limited. Early Voting - all counties are contacted. Election Day - focus is first on vote center counties. ALL PROGRAM TASKS AND OTHER ACTIVITIES NOT ASSOCIATED WITH THE CRISIS ARE SUSPENDED. | See Above - TBD | Summary Actions: SOS Notified OIT Notified Media Relations Activated County Response Team Activated Emergency Conference Call Scheduled Counties Contacted and Instructed to go to County Contingency Plan | SR
SCORE Access | Engility Production Ops verify a major outage impacting more than one county | SCORE @ Engility | 2015-10-12 | 2015-11-03 | Unlikely | Critical | CDOS/Counties/Electors | The mitigation will be like the above mitigation for statewide outage. |  |  | SR
SCORE Access | Engility Production Ops and CDOS IT Ops declare recovery is greater than 30 minutes | SCORE @ Engility | 2015-10-12 | 2015-11-03 | Unlikely | Critical | CDOS/Counties/Electors | The mitigation will be like the above mitigation for statewide outage. |  |  | SR
In Person Voting through the Early Voting module | Screen Freezing | SCORE @ Engility | 2015-10-12 | 2015-11-03 | Likely | Critical | CDOS/Engility/Counties/Electors | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
SCORE Functionality | Functionality within SCORE is broken or incorrect. | SCORE @ SoS | Ongoing | Ongoing | Somewhat Likely | Problematic/Medium | State and County users | Perform mock activities in Sandbox to cofirm SCORE functions correctly prior to major processes. | SCORE Customer Support |  | SR
Daily Processing Mail Ballots | Screen Freezing | SCORE @ SoS | 2015-09-21 | 2015-11-03 | Likely | Problematic | CDOS/Engility/Counties | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
Election Day SCORE Access | Screen Freezing | SCORE @ SoS | 2015-10-12 | 2015-11-03 | Likely | Critical | CDOS/Engility/Counties/Electors | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
SCORE Access at SoS | Internet Failure | SoS Internet | 2015-10-12 | 2015-11-03 | Medium | High | Voters, Media, Counties | Provide failsafe procedures so that SCORE team can access system at another location | Off-site location | Because SCORE is functional in counties, we may wish to enter into an IGA with Denver or other counties | SR
Customer Support | Internet Failure | SoS Internet | 2015-10-12 | 2015-11-03 | Low | Medium | Voters, Media, Counties | Provide failsafe procedures so that front desk can access internet/SCORE through another means | Off-site location |  | SR
SCORE - Daily Data Entry | Screen Freezing |  | 2015-10-12 | 2015-11-03 | Likely | High | CDOS/Engility/Counties | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
SCORE - Daily Data Entry | Connectivity Issues - Random Disconnects |  | 2015-10-12 | 2015-11-03 | Possible | Medium | CDOS/Engility/Counties | SCORE Customer Support takes call/email and escalates to SCORE Manager who in turn escalates to Engility Production Ops and SCORE Management Team. County is required to provide specific information and run the MyConnectionServer test on one pc and provide test numbers that are analyzed by Engility team and IT Security/Network team. Findings are communicated to the county by Customer Support. | Engility Production Ops, SCORE Management Team/Rich Schliep, SCORE Customer Support Team |  | SR
Citrix Server Outage

## Key
Abbreviation Key
ED | Elections Division
VS | Voting Systems
BA | Ballot Access
SR | SCORE
VR | Voter Registration
CPF | Campaign and Political Finance
IT | Information Technology
VSPC | Voter Service and Polling Center
DEO | Designated Election Official
ENR | Election Night Reporting
SoS | Secretary of State